## Summary
| Priority | Initial Estimate | Actual Time Spent | Work Hours Left | Progress
Project 1 | High | 148 | 3 | 0 | 5.405%
Project 2 | Medium | 7 | 7 | 7 | 0%
Project 3 | Medium | 4.5 | 4.5 | 4.5 | 0%
Project 4 | Low | 9 | 9 | 9 | 0%
Extra Mile | Low | 12 | 12 | 12 | 0%
Total |  | 168.5 | 23.5 | 20.5 | 12.77%
Total (+ Extra) |  | 180.5 | 35.5 | 32.5 | 8.451%
Timeframe
Start Date | Deadline | Work Days Left | Weekend Days Left | Total Days Left
2024-01-13 | 2024-03-01 | 32.1429 | 12.6023 | 44.7451
Statistics
Estimated Velocity | Actual Velocity | Velocity needed for deadline | Current Velocity
3.7 h/day | 0.7 h/day | 0.7 h/day | 0.6 h/day
Formulas:
Initial Estimate = MAX(0,([Priority]-TODAY()+1)/7*5)

## Project 1
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Section 1 | 2 | 1 | 0 | Done
Section 2 | 2 | 1 | 0 | Done
Section 3 | 2 | 1 |  | Done
Section 4 | 2 |  |  | Done
Section 5 | 2 |  |  | Not Started
Section 6 | 2 |  |  | Not Started
Section 7 | 2 |  |  | Not Started
Section 8 | 2 |  |  | Not Started
Section 9 | 2 |  |  | Not Started
Section 10 | 2 |  |  | Not Started
Section 11 | 2 |  |  | Not Started
Section 12 | 2 |  |  | Not Started
Section 13 | 2 |  |  | Not Started
Section 14 | 2 |  |  | Not Started
Section 15 | 2 |  |  | Not Started
Section 16 | 2 |  |  | Not Started
Section 17 | 2 |  |  | Not Started
Section 18 | 2 |  |  | Not Started
Section 19 | 2 |  |  | Not Started
Section 20 | 2 |  |  | Not Started
Section 21 | 2 |  |  | Not Started
Section 22 | 2 |  |  | Not Started
Section 23 | 2 |  |  | Not Started
Section 24 | 2 |  |  | Not Started
Section 25 | 2 |  |  | Not Started
Section 26 | 2 |  |  | Not Started
Section 27 | 2 |  |  | Not Started
Section 28 | 2 |  |  | Not Started
Section 29 | 2 |  |  | Not Started
Section 30 | 2 |  |  | Not Started
Section 31 | 2 |  |  | Not Started
Section 32 | 2 |  |  | Not Started
Section 33 | 2 |  |  | Not Started
Section 34 | 2 |  |  | Not Started
Section 35 | 2 |  |  | Not Started
Section 36 | 2 |  |  | Not Started
Section 37 | 2 |  |  | Not Started
Section 38 | 2 |  |  | Not Started
Section 39 | 2 |  |  | Not Started
Section 40 | 2 |  |  | Not Started
Section 41 | 2 |  |  | Not Started
Section 42 | 2 |  |  | Not Started
Section 43 | 2 |  |  | Not Started
Section 44 | 2 |  |  | Not Started
Section 45 | 2 |  |  | Not Started
Section 46 | 2 |  |  | Not Started
Section 47 | 2 |  |  | Not Started
Section 48 | 2 |  |  | Not Started
Section 49 | 2 |  |  | Not Started
Section 50 | 2 |  |  | Not Started
Section 51 | 2 |  |  | Not Started
Section 52 | 2 |  |  | Not Started
Section 53 | 2 |  |  | Not Started
Section 54 | 2 |  |  | Not Started
Section 55 | 2 |  |  | Not Started
Section 56 | 2 |  |  | Not Started
Section 57 | 2 |  |  | Not Started
Section 58 | 2 |  |  | Not Started
Section 59 | 2 |  |  | Not Started
Section 60 | 2 |  |  | Not Started
Section 61 | 2 |  |  | Not Started
Section 62 | 2 |  |  | Not Started
Section 63 | 2 |  |  | Not Started
Section 64 | 2 |  |  | Not Started
Section 65 | 2 |  |  | Not Started
Section 66 | 2 |  |  | Not Started
Section 67 | 2 |  |  | Not Started
Section 68 | 2 |  |  | Not Started
Section 69 | 2 |  |  | Not Started
Section 70 | 2 |  |  | Not Started
Section 71 | 2 |  |  | Not Started
Section 72 | 2 |  |  | Not Started
Section 73 | 2 |  |  | Not Started
Section 74 | 2 |  |  | Not Started

## Project 2
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 | 1 | 1 | Not Started
Task 4 | 1 | 1 | 1 | Not Started
Task 5 | 1 | 1 | 1 | Not Started
Task 6 | 1 | 1 | 1 | Not Started
Task 7 | 1 | 1 | 1 | Not Started

## Project 3
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 0.5 | 0.5 | 0.5 | Not Started
Task 2 | 0.5 | 0.5 | 0.5 | Not Started
Task 3 | 0.5 | 0.5 | 0.5 | Not Started
Task 4 | 0.5 | 0.5 | 0.5 | Not Started
Task 5 | 0.5 | 0.5 | 0.5 | Not Started
Task 6 | 1 | 1 | 1 | Not Started
Task 7 | 1 | 1 | 1 | Not Started

## Project 4
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 3 | 3 | 3 | Not Started
Task 2 | 3 | 3 | 3 | Not Started
Task 3 | 3 | 3 | 3 | Not Started

## Extra Mile
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 2 | 2 | 2 | Not Started
Task 2 | 2 | 2 | 2 | Not Started
Task 3 | 2 | 2 | 2 | Not Started
Task 4 | 2 | 2 | 2 | Not Started
Task 5 | 2 | 2 | 2 | Not Started
Task 6 | 2 | 2 | 2 | Not Started

## Gotchas
When you duplicate a tab, all named ranges will automatically be duplicated as well with name SHEET!ORIGINAL_NAME. In most cases, this is fine and there is nothing explicit you should change in that sheet. What you have to update, though, is the project row in the "Summary" sheet. Use some of the others as reference what to put there.
Renaming a sheet will not break your statistics in the "Summary " sheet.
There is a hidden column D in all your project tabs. It contains some numbers which are used to calcuate remaining and current velocity. Make sure the formulas in those columns are not broken, otherwise your stats will be incorrect.